## Overview
Overview of worksheet content
Version | 1.0 _v.2025-07-19.01
| Name of worksheet | Content of the worksheet | Moisture guide pages*
| 1. Moisture Management | Provides a comprehensive checklist covering background knowledge and practical tips for moisture management in timber construction. This sheet references relevant sections throughout the complete moisture guide. | All pages
| 2. Moisture Management Plan | This plan details the required contents of a moisture management plan, supported by specific examples. The sheet functions as a checklist to ensure all key elements are included when developing a project-specific plan. | Pages 20-45
| 3. Risk Assessment | This sheet provides a framework for the Risk Assessment, which is a key component of the overall Moisture Management Plan. | Pages 28-31
| 4. Control Plans | Outlines the structure and content for key control plans, which are integral parts of the Moisture Management Plan: the Surveillance Plan, Contingency Plan and Maintenance Plan. | Pages 39-43
| 5. Roles and Responsibilities | Provides a template for defining the roles and responsibilities of all project stakeholders, a critical section of the Moisture Management Plan. | Pages 44-45
*Source Document: All page references refer to "Moisture management for timber construction - a practical guide", v.2025-07-19.01.

## 1. Moisture Management
Checklist: Moisture Management in Timber Construction (General practical checklist)
This checklist summarizes best practices for moisture management throughout the project lifecycle.
The pages refer to the relevant sections of the moisture guide.
A. Know Your Material (pages 6-19)
Understand risks (pages 6-13)
Recognise that moisture can lead to mould, decay, structural damage and dimensional changes.
Understand the risk levels associated with different timber moisture contents.
Know how changing humidity and temperature affect timber.
Measure moisture content (pages 16-19)
Use calibrated, appropriate measuring devices with correct settings for timber species and temperature.
Document all moisture readings, protection measures, incidents and corrective actions.
Increase inspection frequency if unsure or after unusual weather events.
Consult a moisture expert for high-risk situations or persistent problems.
B. Pre-construction (pages 20-45)
Plan early (pages 20-21)
Address moisture management in the earliest stages of design and project planning.
Building-Level Considerations (pages 22-25)
Acknowledge that large buildings require more intensive monitoring due to complex elements and numerous contact points.
Map risks in detail for complex designs, identifying all potential moisture entry points and unique challenges.
Plan for continuous protection during long construction phases.
Anticipate increased risk from delayed roofing: plan for temporary covers or phased moisture protection.
Identify materials with low moisture resistance and specify appropriate preventive treatments.
Assess regional and seasonal climate data to develop enhanced moisture management strategies for high-risk locations.
Design-Level Considerations (pages 26-37)
Integrate moisture barriers and membranes correctly to prevent water ingress and avoid trapped moisture.
Design adequate ventilation to allow moisture to escape, especially in enclosed spaces like ventilated façade cavities.
Design effective, sloped drainage systems to manage rainwater and prevent pooling.
Detail connections and horizontal members to ensure water runoff, preventing ingress into joints and pooling on surfaces, particularly vulnerable end-grain.
Avoid or apply special detailing to designs prone to moisture damage, such as flat roofs, roof terraces, unprotected penetrations and CLT in wet rooms.
Integrate thermal insulation without obstructing airflow, using it to prevent condensation.
Design for maintenance, ensuring vulnerable elements are accessible for inspection, repair and replacement.
Design for future climate adaptability, considering potential increases in humidity and extreme weather.
Develop a Moisture Management Plan (pages 20-45, worksheet "2. Moisture Management Plan")
Perform a risk analysis and assess key moisture sources, high-risk assemblies, moisture traps and vulnerable components.
Address all points outlined in the "2. Moisture Management Plan" sheet.
Develop and distribute the "4. Control Plans" and "5. Roles and Responsibilities" documents.
Incorporate contingencies for unexpected events, including extra drying time and enhanced protection.
C. During Construction (pages 14-15, 46-57)
Implement and follow the Moisture Management Plan (page 47)
Correct timber storage (pages 48-49)
Store timber at least 30 cm above the ground on a hard surface.
Protect the stored timber with tarps or covers and ensure good ventilation to prevent moisture entrapment.
Secure all protective coverings to withstand wind and weather.
Immediately remove any standing water from timber surfaces and surrounding areas.
Inspect materials before use visually and measure the moisture content where possible. Wet or damaged materials should be replaced or properly dried.
Protection of timber and other vulnerable materials (pages 14-15, 30-31, 36-37)
Cover the timber structure with temporary roofs and tarps. Never cover wet timber without sufficient ventilation.
Apply end-grain protection like coatings or caps to dry timber.
Seal joints and gaps that are at risk of water ingress and reapply if needed.
Ensure all protective membranes are installed dry, flat, undamaged and with properly sealed joints.
Inspect all weather protection regularly and repair damage immediately.
Ensure timber is verifiably dry before covering or enclosing it (e.g., with plasterboard).
Provide extra protection for highly moisture-sensitive materials during transport, storage and installation.
Scheduled monitoring (pages 40-41, 50-55)
Measure and document moisture content according to the surveillance plan (see sheet "4. Control plans")
Measure moisture at both the surface and core of the timber; document both values.
Prioritise inspections in high-risk areas: bottom of stacks, end grain, joints and horizontal surfaces.
Increase inspection frequency after adverse weather or water ingress events.
Verify that any installed moisture sensors are functional and recording data.
Take immediate action if measured moisture content exceeds accepted limits.
Regular progress reviews (pages 44-45)
Schedule regular meetings to review moisture management performance and address any challenges.
Quick reaction to water ingress (pages 42, 56-57)
Respond immediately to any sign of water ingress by activating the contingency plan (see sheet "4. Control Plans").
Ensure necessary resources, such as dehumidifiers, ventilation fans for increased airflow and additional coverings, are readily available.
Involve a moisture expert early if faced with high moisture content, suspected mould, or persistent issues
Involve a moisture expert early if facing high moisture content or suspected mould.
Allow affected timber adequate time to dry before permanent covering or enclosing. If needed, clearn, dry, remediate or replace the timber as per plan.
Documentation (pages 39-57)
Keep a detailed log of all moisture-related activities as measurements, weather events, incidents and sensor alerts and remediation steps.
Require the entire team to report and document moisture issues as they arise.
D. Post-Construction / Occupancy (pages 43, 58-59)
Continue to follow the Moisture Management Plan
Transfer the maintenance plan to the building owner, including a schedule for periodic inspections.
Ensure installed sensors are actively monitored and maintained, with clear protocols for responding to alerts.
Keep all moisture management records updated and accessible.
E. Continuous Improvement (pages 44-45)
Establish a feedback loop with all stakeholders to review the moisture strategy's effectiveness and identify improvements.
Provide ongoing training for construction and maintenance personnel on best practices.
Regularly update the moisture management plan based on lessons learned, new technologies and materials.
Organise knowledge sharing sessions with project teams to share lessons learned and improve future projects.

## 2. Moisture Management Plan
Create a Moisture Management Plan (MMP)
Use this checklist when developing the Moisture Management Plan to ensure all required aspects are addressed.
The following questions help define the overall moisture management approach.
The pages refer to the relevant sections of the moisture guide.
A. Moisture Management Strategy
What are you planning to construct?
Is it a large or small building? Larger buildings generally present greater moisture risk.
How many storeys will the building have? Taller structures typically carry higher moisture exposure risk.
Will the building have a flat roof? If yes, this increases the risk of water retention.
Is structural timber used in wet areas such as bathrooms? If yes, this raises the moisture risk, so consider alternative materials.
Is structural timber located below ground level? If yes, this presents a very high moisture risk, so redesign is recommended.
Construction schedule and weather risk:
What is the total duration of the construction process?
How tight is the construction schedule? Tighter schedules require greater protection measures, as drying after wetting takes time.
How long will each floor remain exposed to weather before enclosure?
Can installation of moisture-sensitive materials be avoided during poor weather?
When are timber components scheduled for delivery? Aim for just-in-time delivery.
If just-in-time delivery is not feasible, can deliveries be split into smaller, manageable batches?
During which seasons will construction take place? Assess expected rainfall, temperature and humidity conditions.
Have indoor climate variations (e.g. from heating) been considered in addition to external weather?
Will the weather forecast be monitored daily throughout the construction period?
Identify all relevant moisture sources as rain, site storage, ground moisture, wet concrete etc.
Storage
Where will timber and other moisture-sensitive materials be stored on site?
Is there adequate space to keep all stored materials dry?
What is the condition and type of the ground surface designated for material storage?
Are contingency storage options available in the event of construction delays?
How is the storage area ventilated?
Construction principles
Should components be installed horizontally or vertically to reduce water ingress?
Is there adequate space to protect the full site with weatherproofing?
Is there enough clearance for cranes and efficient material handling?
How will large or prefabricated components be moved and installed?
What assembly method will be used? Are any joints especially vulnerable?
What types of timber materials will be used: solid wood, panels, CLT, glulam, etc.? How resistant are they to moisture?
Are joints, gaps and cracks designed to shed water, or are they likely to trap moisture?
Will any timber come into direct contact with high-moisture materials such as humid concrete? Will a membrane or barrier be used?
Are drainage routes in place during the construction phase?
Has the timber been specified and ordered at the correct moisture content for its intended use?
Are timber components conditioned to the correct moisture content before being enclosed?
B. Risk Assessment & Protection Strategy
Construction site protection
Which type of temporary building cover will be used?
Assess the overall moisture exposure for the full construction site. Refer to sheet “3. Risk Assessment, Table 1”.
Individual components
Prepare a complete list of all individual components
Define the moisture protection measures and expected duration for each construction phase (transport, storage, installation, exposure during ongoing works) and for every component
Assess the moisture exposure of each component during the respective construction phases. Refer to sheet “3. Risk Assessment, Table 1”
Assess the moisture vulnerability of each component. Refer to sheet “3. Risk Assessment, Table 2”.
Categorise each component into a risk class (RC1, RC2 or RC3). Use "3. Risk Assessment, Table 3".
Document the selected temporary moisture protection method for each component throughout the construction phases.
Document the results as outlined in sheet “4. Control plans, Surveillance plan”.
C. Additional Proactive Strategies
Plan temporary drainage for rainwater and groundwater
Identify all interfaces between components
Identify all potential water ingress points in the construction, as rain, high relative humidity, condensation on cold bridges etc.
Check if timber components or interfaces are at risk of getting wet
For each identified risk, define appropriate protection, as tape, tarp, membranes etc.
Reassess water flow and exposure after applying the additional protection
For each component identified as being at risk, define additional protection, as end-grain sealing, membranes, edge wrappingetc.
Document all protection in "4. Control plans, Surveillance plan"
D. Surveillance Plan
Planning for controls and documentation (see sheet "4. Control Plans, Surveillance plan")
What format will be used for documentation and if relevant, which digital platform? The more detail provided regarding measurements and locations, the better the traceability.
Who is designated as the moisture manager?
List all construction phases and the corresponding components to be monitored. Refer to your risk assessment.
What is the risk class of each component during the respective construction phase? Refer to your risk assessment.
Which moisture protection method has been selected? Refer to your protection strategy.
Select the moisture measurement method, as handheld resistance moisture meter, fixed sensor with or without data logging, visual inspection for leaks and staining, etc.
How frequently should inspections be conducted during each construction phase?
Define the measurement locations: depth and specific position on each component.
Define how many measurements are required per delivered batch and per component type.
What are the acceptable lower and upper limits for moisture content?
Who will be responsible for taking the measurements?
During ongoing construction
Document all measured moisture values
Confirm whether each measurement falls within the specified moisture limits
If a measurement exceeds limits, record the corrective action taken. Refer to sheet "4. Control Plans, Contingency Plan".
Document the name of the person who carried out the measurement.
Record the date of the measurement.
E. Contingency Plan / Emergency Procedures
Planning for potential contingencies
Determine the format and digital platform to be used for documenting contingency actions. The more detail recorded about the incident, the better the traceability.
Identify all types of potential moisture-related incidents or failures that could occur during construction.
Define the specific contingency scenarios that may apply to the project.
Outline the required actions for each scenario in chronological order and assign clear responsibilities.
Ensure that all roles and responsibilities are clearly communicated to relevant personnel in advance.
During ongoing construction
Respond to incidents without delay and follow predefined procedures.
Record the nature of the event that occurred, including a clear description.
Document the exact location where the event took place.
Specify which materials were affected and to what extent.
Record the actions taken, referencing the relevant predefined contingency scenario.
F. Maintenance and Long-Term Moisture Management
Provide the owner with instructions
Write a maintenance plan that includes routine moisture management procedures and an inspection schedule for the operational phase.
If moisture sensors have been installed, hand over full documentation of installation locations and alert settings.
Include guidance for regular checks of sensor accuracy and system functionality.
Establish clear procedures for responding to sensor alerts along with defined responsibilities for inspection and corrective actions.
Monitor weather and indoor climate conditions including relative humidity and temperature. Ensure ventilation is sufficient to maintain indoor relative humidity between 30% and 65%.
Provide a quick-response plan to address any moisture-related issues or emergencies.
Maintain a procedure for documenting all maintenance and inspection activities related to moisture management.
G. Roles and Responsibilities
Define roles and responsibilities
List the names and associated companies responsible for each role as outlined in sheet "5. Roles and Responsibilities".
Include any individuals or teams with responsibilities related to moisture management to ensure they receive the most up-to-date versions of the plan.
Keep the list current and update it promptly in the event of personnel or contractor changes.
H. Documentation
Describe record-keeping
Specify the formats and platforms to be used for logging moisture measurements, corrective actions and internal communications.
Integrate with QA
Where applicable, link the moisture management plan to existing quality assurance systems to avoid duplication and improve accountability.
External audit of moisture practices
Appoint qualified external professionals to carry out periodic audits of the moisture management procedures. Their task is to verify compliance and suggest improvements in line with current industry standards and best practices.

## 3. Risk Assessment
Risk Assessment
Conduct a risk assessment of the overall construction and each type of component based on its exposure and component vulnerability.
Table 1
| 1. Use Table 1 to specify the "Exposure to moisture". In cases of doubt, select the higher class. 2. Use Table 2 to define the "Component vulnerability". In cases of doubt, select the higher class. 3. Use the "Risk matrix" to determine the risk classes based on "Exposure to moisture" and "Component vulnerability". 4. Use Table 3 for recommended actions and protective measures for each component in each defined exposure. 5. Document the decisions in worksheet "4. Control plans" | [7 empty] | Exposure to moisture
[9 empty] | Low | Medium | High
[8 empty] | Transport and storage | Just-in-time delivery / packaged or covered during transport / stored dry, ventilated, no risk of leakage | Delivered in small batches / packaged or covered during transport / stored dry, ventilated, little risk of leakage | Delivered in bigger batches / risk of exposure during transport / storage under suboptimal conditions
[8 empty] | Exposure to weather on site | Construction is carried out under full protection, e.g. in a factory and/or under total enclosure | Construction site bears a risk of occasional climatic exposure, e.g. materials are only protected by a temporary cover while the building itself is not covered yet | Significant risk of climatic influence, e.g. no cover of installed building materials
[8 empty] | Exposure to humidity | Construction process does not include water- or moisture-containing building materials like drying concrete or other construction products with elevated moisture content (with a moisture content not higher than that corresponding to 75% relative humidity) | Construction process involves intended but limited water or moisture content in building materials, e.g. self-drying concrete, covered hardening concrete, membranes installed against water ingress | Construction process involves significant water or moisture content in building materials, e.g. casting of concrete, extra humidification
| Table 2 | [5 empty] | Risk matrix |  |  |  |  | Table 3
|  |  | Type of component | Example component (based on ability to absorb moisture) | Risk of mould growth | Amount of drying time allocated (situational vulnerability) |  |  | Exposure to moisture |  |  | Actions and recommended protective measures
[9 empty] | Low | Medium | High | Risk class | Actions and protective measures | Pay attention to
| Component vulnerability | Low | Materials that do not absorb moisture | Glass, steel | Almost no risk | Adequate amount of drying time allocated | Component vulnerability | Low | 1 | 1 | 2 | 1 | • Moisture content measurements at critical times • Proper storage with sufficient ventilation • Air flow around load-bearing structures during construction until dry • Tapes on floor joints • Drip-edge on cladding • Sufficient ground clearance for cladding • Adequate cover of materials and building site | • Installation of fasteners in cladding not too deep • Repair tapes on joints if damaged • Removal of standing water in construction site and on materials
|  | Medium | Timber with possibility for drying | Solid timber, CLT, glulam, cladding | Some risk | Tight schedule, but drying given priority |  | Medium | 1 | 2 | 3 | 2 | In addition to all points in RC 1: • Continuous moisture content measurements • Weather protection through timber treatments, membranes and tarps. Regular inspection and maintenance of those. • Tapes and membranes on all joints • End-grain sealing on all exposed timber • Use membranes to separate from wet materials like cast concrete • Schedule just-in-time deliveries and/or storage under roof | In addition to all points in RC 1: • Adequate levels of moisture content before installation • Assessment of specific potential moisture problems • Sufficient drying time if moisture content is too high For components of high vulnerability: • Ensure they never come in contact with water and are not stored in a humid climate • Ensure weather protection is used and is intact at all times (during transport, storage and installation)
|  | High | Materials that absorbs moisture quickly and cannot dry without damage | Prefabricated floor, roof, or facade elements, box modules, wood-based panels (e.g. MDF, OSB, plywood), mineral-based or biobased insulation, gypsum boards | High risk | Tight schedule, difficult to achieve sufficient drying |  | High | 2 | 3 | 3 | 3 | In addition to all points in Risk Class 1 and 2: • Engage a moisture expert already during design (pre-construction) • Conduct moisture calculations or simulations during design | All points in Risk Class 1 and 2
Engage a moisture expert

## 4. Control plans
Control plans
Italic text provides examples and recommendations. This content should be adapted for each specific project
Surveillance plan (page 40)
Written by, Company, Date: | Mr. X, Company Y, 13-11-2024
This plan should be filled in before construction begins. | [9 empty] | The measurement results are to be filled in as they are taken.
Moisture manager: | Jane Doe, Company Z | [8 empty] | Check if within requirements (see moisture guide for reference)
Phase | What? | Risk class (from Risk assessment) | Protection | Measurement tool (see guide for reference) | Schedule for moisture content measurements | Measurement location (see guide for reference) | Number of measurements (see guide for reference) | Requirement | Responsible stakeholder for measurements | Surface measurement or check | If no, list action and responsible | Responsible for check | Date of check
Materials upon arrival | Glulam beams | Risk class 2 | Transported material covered | Resistance moisture meter with insulated needles | per arriving delivery | - 15cm from end grain - mid-length | 2/20 | 8-16% Moisture content (MC) | Company X | Measured value for each location. Fulfilled yes/no | - | John Doe, Company X | 2025-01-26
… (list of all delivered components and materials)
Storage on site | columns | Risk class 3 | Storage outside under tent | Visual inspection | every week | - |  | cover intact, no leaks, no standing water on floor | Company X | Measured value. Fulfilled yes/no | - | John Doe, Company X | 2025-02-25
… (list of all stored components and materials)
Directly before installation | CLT wall | Risk class 2 | Covered from storage location to construction site | Resistance moisture meter with insulated needles | each installation day | - 15cm from end grain - mid-length | 1/5 | 8-16% MC | Company X | Measured value for each location. Fulfilled yes/no | - | John Doe, Company X | 2025-03-24
… (list of all components and materials to be installed)
During ongoing construction | CLT floor slab | Risk class 3 | End grain sealant or cover and protective membrane | Capacitance moisture meter | every week | - top floor slab - mid floor slab - lowest CLT floor slab | 1/10 | 8-16% MC | Company X | Measured value for each location. Fulfilled yes/no | - | John Doe, Company X | 2025-04-23
… (list of all installed components and materials)
Permanent covering | CLT wall | Risk class 2 | Installed under full site cover | Resistance moisture meter with insulated needles | before enclosing materials | - 15cm from end grain - mid-length | 1/10 | 8-16% MC | Company X | Measured value for each location. Fulfilled yes/no | Jane Doe was informed and given information on specific location, values and history | John Doe, Company X | 2025-04-22
… (list of all components and materials to be enclosed)
… (additional phases) | … | … | … | … | … | … | … | … | … | … | … | … | …
Contingency plan (page 42)
Written by, Company, Date: | Mr. X, Company Y, 13-11-2024
Filled in BEFORE event occured, before the start of construction:
Moisture manager: | Jane Doe, Company Z
Potential event | Rain water ingress | Responsible | Ground water ingress | Responsible | Pipe leakage | Responsible | … (add all potential events) | Responsible
Phase | Material during storage | - | Building during ongoing construction | - | After permanent covering | - |  | -
Action plan:
1. Direct action | Inform moisture manager | First responder | Inform moisture manager | First responder | Inform moisture manager | First responder
| Stop additional ingress | Company X, instructed by moisture manager | Stop additional ingress | Company X, instructed by moisture manager | Stop additional ingress | Company X, instructed by moisture manager
| Remove standing water | Company X, instructed by moisture manager | Remove standing water | Company X, instructed by moisture manager | Remove standing water. Remove all affected and dismountable components to access the area (insulation, plasterboards, etc.) | Company X, instructed by moisture manager
2. Inspection | Find the origin and reason for ingress | Moisture manager | Find the origin and reason for ingress | Moisture manager | Analyse runways of water. Pay special attention to discolourations and hidden gaps/joints | Moisture manager
|  |  | Check membranes towards ground | Moisture manager | Find the origin and reason for the leakage | Moisture manager
3. Additional measurements | Measure moisture content. Schedule additional measurements continuing for several days and document values. | Company X, instructed by moisture manager | Measure moisture content. Schedule additional measurements continuing for several days and document values. | Company X, instructed by moisture manager | Measure moisture content. Schedule additional measurements continuing for several days and document values. | Company X, instructed by moisture manager
|  |  | Add affected material to the routine surveillance plan | Moisture manager | Add affected material to the routine surveillance plan | Moisture manager
4. Action plan | Consult moisture expert in any case of doubt and/or at high moisture content | Moisture manager contacts moisture expert | Consult moisture expert in any case of doubt and/or at high moisture content | Moisture manager contacts moisture expert | Consult moisture expert in any case of doubt and/or at high moisture content | Moisture manager contacts moisture expert
| Improve the cover to avoid the same event repeating. Check if other areas are at risk for the same issue. | Company X, instructed by moisture manager | Dry the affected materials to required moisture content before encapsulating. Adjust time schedule if necessary. | Project manager | Check if other areas are at risk for the same issue. | Company X, instructed by moisture manager
| Ensure good ventilation for drying | Company X, instructed by moisture manager | Check if other areas are at risk for the same issue. | Company X, instructed by moisture manager | Dry the affected materials to required moisture content before encapsulating. Check if there is sufficient ventilation. Adjust time schedule if necessary. | Project manager
| Dry the affected materials to required moisture content before encapsulating. Adjust time schedule if necessary. | Project manager
5. Control | Check if the actions are implemented and successful | Moisture manager | Check if the actions are implemented and successful | Moisture manager | Check if the actions are implemented and successful | Moisture manager
… (additional actions) | … | … | … | … | … | … | … | …
Fill in AFTER event occurred:
| Theoretical steps (from contingency plan | Practical steps | Theoretical steps (from contingency plan | Practical steps
Occurred event | Rain water ingress in material storage | The tarp of an improvised tent covering CLT was blown away during a heavy storm | … (add more events as they occur) | …
Location and time | Small storage tent, 24-05-2025 | CLT was stored outside on 30cm high supports, covered by a tent made from tarp
Affected area or materials | - | 15 stored CLT slabs
Action plan:
1. Direct action | Inform moisture manager | Jane Doe was informed upon discovery of damage at 9:00 and arrived to check before noon
| Stop additional ingress | The rain had already stopped when the issue was discovered
| Remove standing water | Water on top of the CLT got removed with a broom
2. Inspection | Find the origin and reason for ingress | The tarp was not fastened properly and blew away under strong wind.
3. Additional measurements | Measure moisture content. Schedule additional measurements continuing for several days and document values. | The moisture content got checked with a moisture meter. On the surface of the top CLT slab the MC was >30% on the surface and 24% in 4cm depth. A lower CLT slab showed a value of 20% on the exposed side and 18% in 4cm depth. The measurements will be repeated every monday, wednesday and friday, until all moisture content values are below 18%.
4. Action plan | Consult moisture expert in any case of doubt and/or at high moisture content | The moisture manager called the moisture expert for advice. For future storage, better tents will be ordered.
| Improve the cover to avoid the same event repeating. Check if other areas are at risk for the same issue. | The undamaged parts of the tarp were attached with staples and ties to secure against wind. The damaged parts of the tarp were replaced. The other storage tents were adjusted likewise.
| Ensure good ventilation for drying | The tents have ventilation gaps in the bottom and small battens are placed in between the individual slabs.
| Dry the affected materials to required moisture content before encapsulating. Adjust time schedule if necessary. | The slabs will not be installed until the moisture content is <16%. The installation schedule got delayed by 3 weeks.
5. Control | Check if the actions are implemented and successful | The desired moisture content was reached after 14 days.
Maintenance plan (page 43)
Written by, Company, Date: | Mr. X, Company Y, 13-11-2024
Filled in before start of construction:
Task: | Schedule | Responsible
Visual inspection for discolourations or moisture | Annually | Facility manager, as instructed by building owner
Monitor moisture sensor measurements | Automatic notifications recommended. Check functionality annually. | Facility manager, as instructed by building owner
Weather monitoring in case of extreme weather | Ongoing | Building owner, facility manager
Indoor climate and ventilation, ensure balanced temperature and humidity within limits | Daily | Building occupant
Update emergency phone list | Annually | Building owner
Document actions | Ongoing, when actions are taken | Building owner, facility manager

## 5. Roles and Responsibilities
Roles and Responsibilities
Roles and responsibilities for Diagram 1. Planning phase (see reference in moisture guide)
Involved project partners
| Architect | Engineer | Contractor | Building Owner | ….
Contact person | Jane Doe
Company | Company x
Contact info | …
Involvement in the following plans: | Moisture management plan, risk assessment | Moisture management plan, risk assessment | Moisture management plan, risk assessment, all control plans | Maintenance plan
… (additional fields)
Responsible
| Responsible for moisture management planning | Moisture expert, advisor
Contact person | Jane Doe | Joe Doe
Company | Company x | Company y
Role | Moisture manager | External expert
Contact info | … | …
Responsible for the following | Moisture management plan, risk assessment, surveillance plan, contingency plan, maintenance plan, roles and responsibilities | Reviewing the moisture management plan
… (additional fields)
Roles and responsibilities for Diagram 2. Construction phase (see reference in moisture guide)
Involved responsible project partners
| Project manager | Moisture manager, responsible for control and contingency | External advisor: Moisture expert (if needed)
Contact person |  |  | Joe Doe
Company |  |  | Company x
Contact info |  |  | …
Involvement in the following plans: | Moisture management plan, risk assessment, surveillance plan, contingency plan, maintenance plan, roles and responsibilities | Moisture management plan, risk assessment, surveillance plan, contingency plan, maintenance plan | Reviewing the moisture management plan, surveillance plan, contingency plan, maintenance plan. Advising for issues occurring during construction.
… (additional fields)
Involved stakeholders
| Control at delivery | Control before installation | Regular control | Control before closure | Contingency
Contact person
Company
Contact info
Involvement in the following plans: | Surveillance plan | Surveillance plan | Surveillance plan | Surveillance plan | Contingency plan
… (additional fields)
External advisors
| Mitigation of moisture ingress | Mould experts | Removal of mould | … (additional topics)
Contact person
Company
Contact info
Involvement in the following plans: | Moisture management plan, contingency plan | Surveillance plan, contingency plan | Surveillance plan, contingency plan
… (additional fields)